## IPDS
Número | Costo | Descripción | Avance % | Avance $ | Facturado $ | Facturado %
2 | 935 | TC1000 | 0% | 0
3 | 4572 | Frypack | 100% | 4572
4 | 312 | MAPA | 100% | 312
5 | 6339 | Palitos 2 | 100% | 6339
6 | 8001 | Palitos 3 | 100% | 8001
7 | 3325 | PC32 | 100% | 3325
8 | 1039 | Schaaf1 | 100% | 1039
9 | 4364 | PC32 Flex | 75% | 3273
10 | 3950 | Schaaf2 | 100% | 3950
11 | 104 | Haloila | 100% | 104
12 | 208 | Control Aceite naves 1-4 | 100% | 208
13 | 935 | Control Aceite naves 5-6 | 100% | 935
14 | 623 | Planta de almidón | 100% | 623
15 | 416 | Control agua nave 5 | 100% | 416
16 | 416 | Control Agua nave 6 | 100% | 416
17 | 3637 | Planta tratamiento de efluentes | 100% | 3637
18 | 104 | Control Bombas cisterna | 100% | 104
Total MO | 39280 | Avance MO | 94.84% | 37254 | 39280 | 100%
Mat | 13410 | Hardware | 100% | 13410 | 13410
Total | 52690 | Avance TOTAL | 96.15% | 50664 | 52690 | 100%

## IDFs
IDF | Ubicación | Alcance | Comentario | Plan | Asignado IPs | Cambio realizado | Conexionado | Prueba conexión | Documentado
IDF1 | Sala tableros MAPA | Schaaf 1 - Empaque | OK | OK | OK | OK | OK | OK
|  | Schaaf 1 - Extrusor 1200 | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 1 - Mixer 1200 | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 1 - Extrusor 925 | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 1 - Spray Dynamics | OK | OK | OK | OK |  |  | OK
|  | PC32 - Proceso | OK | OK | OK | OK | OK | OK | OK
|  | PC32 - Sazonado | OK | OK | OK | OK | OK | OK | OK
|  | PC32 - Descarga papa | OK | OK | OK | OK | OK | OK | OK
|  | Planta Almidón | OK | OK | OK | OK | OK | OK | OK
|  | Mantenimiento | Futuro | Futuro | Futuro | Futuro | Futuro | Futuro | Futuro
|  | MAPA | OK | OK | OK | OK | OK | OK | OK
IDF2 | Sala tableros Doritos | TC1000 - Cocimiento |  | Agregar NATR | OK
|  | TC1000 - Proceso |  | Agregar NATR | OK
|  | TC1000 - Enzima |  | Agregar NATR | OK
|  | Schaaf 2 - Empaque | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 2 - Horno | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 2 - Mixer 1200 | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 2 - Extrusor 1200 | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 2 - Mixer 925 | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 2 - Extrusor 925 | OK | OK | OK | OK | OK | OK | OK
|  | Schaaf 2 - Spray Dynamics | OK | OK | OK | OK | OK | OK | OK
|  | PC32 - Empaque | OK | OK | OK | OK | OK | OK
|  | Haloila 1 | OK | OK | OK | OK | OK | OK | OK
|  | Haloila 2 | Futuro | Futuro | OK | Futuro | Futuro | Futuro | Futuro
|  | Palitos 2 - Sazonado | OK | OK | OK | OK | OK | OK | OK
|  | Palitos 2 - Proceso | OK | OK | OK | OK | OK | OK | OK
|  | Palitos 2 - Empaque | Futuro | Futuro | Futuro | Futuro | Futuro | Futuro | Futuro
IDF3 | Sala tableros Nave5/Nave6 | PC32 Flex - Empaque | OK | OK | OK | OK | OK | OK | OK
|  | Palitos 3 - Freidor | OK | OK | OK | OK | OK | OK | OK
|  | Palitos 3 - Amasadora | OK | OK | OK | OK | OK | OK | OK
|  | Palitos 3 - Laminado | OK | OK | OK | OK | OK | OK | OK
|  | Palitos 3 - Empaque | OK | OK | OK | OK | OK | OK | OK
|  | Palitos 3 - Marmitas | OK | OK | OK | OK | OK | OK | OK
|  | Control Agua Nave 6 | OK | OK | OK | OK | OK | OK | OK
|  | Frypack - Proceso | OK | OK | OK | OK | OK | OK | OK
|  | Frypack - Empaque | OK | OK | OK | OK | OK | OK | OK
|  | Frypack - Spray Dynamics |  | Migración PLC y HMI | OK
IDF4 | Oficina WWTP | WWTP | OK | OK | OK | OK | OK | OK | OK
|  | Control Tanques Azules | OK | OK | OK | OK | OK | OK | OK
IDF5 | Sala tableros PC32 Flex | PC32 Flex - Proceso |  | Agregar NATR | OK
|  | Control Agua Nave 5 | OK | OK | OK | OK | OK | OK | OK
|  | Control Aceite Nave5-Nave6 | OK | OK | OK | OK | OK | OK | OK
|  | Control Aceite Nave1-Nave4 | OK | OK | OK | OK | OK | OK | OK

## Aceite N1-4
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
AceiteN1 | AceiteN1 | AceiteN1-PLC |  |  | PLC |  | 11.18.55.24 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN1 | AceiteN1 | AceiteN1-HMI |  |  | HMI |  | 11.18.55.25 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN1 | AceiteN1 | AceiteN1-OIT |  |  | PC |  | 11.18.55.26 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5

## Aceite N5-6
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
AceiteN5 | AceiteN5 | AceiteN5-PLC | 1769-L30ER | 30.011 | PLC | 192.168.1.110 | 11.18.55.15 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-HMI1 | 2711P-T10C22D9P | 12 | HMI | 192.168.1.114 | 11.18.55.16 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-HMI2 | PVP6 700 | 12 | HMI | 192.168.1.245 | 11.18.55.17 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-BBA_GIRASOL_N5 | PF525-EENET |  | VFD | 192.168.1.111 | 11.18.55.18 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-BBA_HOSO_N5 | PF525-EENET |  | VFD | 192.168.1.112 | 11.18.55.19 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-BBA_DESECHO_N5 | PF525-EENET |  | VFD | 192.168.1.113 | 11.18.55.20 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-BBA_GIRASOL_ALMACEN | PF525-EENET |  | VFD | 192.168.1.115 | 11.18.55.21 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-BBA_HOSO_ALMACEN | PF525-EENET |  | VFD | 192.168.1.116 | 11.18.55.22 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
AceiteN5 | AceiteN5 | AceiteN5-Remote_Almacen | 1734-AENTR |  | IO | 192.168.1.117 | 11.18.55.23 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5

## Agua N5
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Agua Nave 5 | Agua Nave 5 | AguaNave5-PLC | 1769-L30ER | 30011 | PLC | 192.168.1.50 | 11.18.55.11 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
Agua Nave 5 | Agua Nave 5 | AguaNave5-HMI | PVPlus 7 1000 | 12 | HMI | 192.168.1.125 | 11.18.55.12 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
Agua Nave 5 | Agua Nave 5 | AguaNave5-Bomba_1 | PF525 | 5.001 | VFD | 192.168.1.51 | 11.18.55.13 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
Agua Nave 5 | Agua Nave 5 | AguaNave5-Bomba_2 | PF525 | 5.001 | VFD | 192.168.1.52 | 11.18.55.14 |  | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5

## Agua N6
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Agua Nave 6 | Agua Nave 6 | AguaNave6-PLC | 1769-L30ER | 20.12 | PLC | 192.168.1.100 | 11.18.54.11 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Agua Nave 6 | Agua Nave 6 | AguaNave6-HMI | 2711P-T10C21D8S | 12 | HMI | 192.168.1.101 | 11.18.54.12 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Agua Nave 6 | Agua Nave 6 | AguaNave6-Bomba_1 | PF525 | 5001 | VFD | 192.168.1.102 | 11.18.54.13 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Agua Nave 6 | Agua Nave 6 | AguaNave6-Bomba_2 | PF525 | 5001 | VFD | 192.168.1.103 | 11.18.54.14 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3

## Almidón
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Almidón | Almidón | Almidon-PLC | 1769-L32E | 20.13 | PLC | 130.130.130.160 | 11.18.53.11 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Almidón | Almidón | Almidon-HMI | 2711P-T7C21D8S | 5.1 | HMI | 130.130.130.235 | 11.18.53.12 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Almidón | Almidón | Almidon-M221 | PF525 | 5001 | VFD | 130.130.130.163 | 11.18.53.13 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Almidón | Almidón | Almidon-M262 | PF525 | 5001 | VFD | 130.130.130.164 | 11.18.53.14 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Almidón | Almidón | Almidon-M321 | PF525 | 5001 | VFD | 130.130.130.165 | 11.18.53.15 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Almidón | Almidón | Almidon-M362 | PF525 | 5001 | VFD | 130.130.130.166 | 11.18.53.16 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1

## Frypack
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Frypack | Proceso | ProcesoFrypack-PLC | 1769-L33ER | 24.11 | PLC | 100.100.100.101 |  | 11.18.54.81 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | Proceso | ProcesoFrypack-HMI1 | PVP7 Performance |  | HMI | 100.100.100.104 |  | 11.18.54.82 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | Proceso | ProcesoFrypack-HMI2 | PVP7 Performance |  | HMI | 100.100.100.105 |  | 11.18.54.83 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | Proceso | ProcesoFrypack-SWITCH | 1783-BMS10CGN |  | SWITCH | 100.100.100.60 |  | 11.18.54.84 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | SprayD | SprayDFrypack-PLC |  |  | PLC |  | 11.18.54.101 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | SprayD | SprayDFrypack-HMI |  |  | HMI |  | 11.18.54.102 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | Empaque | EmpaqueFrypack-PLC | 1768-L43 |  | PLC | 100.100.100.101 |  | 11.18.54.103 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | Empaque | EmpaqueFrypack-OIT(Host) | PC |  | PC | DHCP | 100.100.100.91 | 11.18.54.104 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | Empaque | EmpaqueFrypack-OIT(VM) | PC |  | PC | 100.100.100.140 | 100.100.100.90 | 11.18.54.105 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Frypack | Empaque | EmpaqueFrypack-SWITCH |  |  | SWITCH | 100.100.100.60 |  | 11.18.54.106 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3

## Haloila
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Haloila 1 | Haloila 1 | Octopus_Twin | 5069-L306ER | 31.011 | PLC | DHCP | 11.18.53.139 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloila 2 | Haloila 2 | Octopus_Twin |  |  |  |  | 11.18.53.140 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Obin | Switch NATR 1783 | 1783- NATR |  |  | 192.168.0.199 | 11.18.53.181 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Ketan | PLC-2 AB 850 Ketan |  |  |  | 192.168.0.202 | 11.18.53.182 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Ketan | PLC-1 AB 850 Ketan |  |  |  | 192.168.0.200 | 11.18.53.183 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Ketan | PC Industrial |  |  |  | 192.168.0.210 | 11.18.53.184 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Ketan | OIT-1 Ketan |  |  |  | 192.168.0.201 | 11.18.53.185 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Ketan | OIT-2 Ketan |  |  |  | 192.168.0.203 | 11.18.53.186 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Obin | PLC Obin | 5069-L306ER | 35 | PLC | 192.168.0.244 | 11.18.53.187 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Obin | OIT -1 AB Panel View |  |  |  | 192.168.0.20 | 11.18.53.188 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Obin | OIT -2 AB Panel View |  |  |  | 192.168.0.21 | 11.18.53.189 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Haloia 1 | Obin | OIT -3 AB Panel View |  |  |  | 192.168.0.22 | 11.18.53.196 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2

## MAPA
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
MAPA | Linea | MAPA-PLC | 1756-EN2T |  | PLC |  | 11.18.53.60 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
MAPA | Linea | MAPA-OIT | PC |  | PC |  | 11.18.53.61 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
MAPA | Linea | MAPA-OIT-M-PRIMA | PC |  | PC |  | 11.18.53.62 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
MAPA | Linea | MAPA-OIT-ROTOVARIO | PC |  | PC |  | 11.18.53.63 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1

## Palitos 2
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Palitos 2 | Línea | Palitos2-PLC | 1769-L33ER | 31.011 | PLC | 130.130.130.1 |  | 11.18.53.190 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Palitos 2 | Línea | Palitos2-HMI-Amasadora | PVP7 700 | 12 | HMI | 130.130.130.4 |  | 11.18.53.191 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Palitos 2 | Línea | Palitos2-HMI-Freidor | PVP6 1000 | 12 | HMI | 130.130.130.5 |  | 11.18.53.192 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Palitos 2 | Línea | Palitos2-Switch | 1783-BMS10CGN |  | SWITCH |  | 130.130.130.101 | 11.18.53.193 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Palitos 2 | Sazonado | SazonadoPalitos2-PLC |  |  | PLC |  |  | 11.18.53.195 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2

## Palitos 3
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Palitos 3 | Amasadora | AmasadoraP3-PLC | 5069-L306ER |  | PLC | 192.168.1.14 | 11.18.54.15 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Amasadora | AmasadoraP3-HMI 1 | 2711P-T7C21D8S | 12 | HMI | 192.168.1.100 | 11.18.54.16 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Amasadora | AmasadoraP3-HMI 2 | 2711P-T7C21D8S | 12 | HMI | 192.168.1.101 | 11.18.54.17 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Amasadora | AmasadoraP3-Reserva |  |  |  |  | 11.18.54.18 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Amasadora | AmasadoraP3-Reserva |  |  |  |  | 11.18.54.19 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Amasadora | AmasadoraP3-Reserva |  |  |  |  | 11.18.54.20 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Marmitas | MarmitasP3-PLC | 2080-LC50-24QWB |  | PLC | 130.130.130.75 | 11.18.54.21 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Marmitas | MarmitasP3-HMI | 2711-T4T | 5.011 | HMI | 130.130.130.76 | 11.18.54.22 |  | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Laminado | LaminadoP3-PLC | 1769-L33ER | 28.012 | PLC | 192.168.1.1 |  | 11.18.54.23 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Laminado | LaminadoP3-HMI1 |  |  | HMI | 192.168.1.101 |  | 11.18.54.24 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Laminado | LaminadoP3-HMI2 |  |  | HMI | 192.168.1.102 |  | 11.18.54.25 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Laminado | LaminadoP3-NATR | 1783-NATR |  | SWITCH |  | 192.168.1.5 | 11.18.54.27 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Freidor | FreidorP3-PLC | 1769-L33ER | 24.11 | PLC | 100.100.100.101 |  | 11.18.54.47 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Freidor | FreidorP3-HMI1 | PVP7 Performance 1000 | 12 | HMI | 100.100.100.104 |  | 11.18.54.48 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Freidor | FreidorP3-HMI2 | PVP7 Performance 1000 | 12 | HMI | 100.100.100.105 |  | 11.18.54.49 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Freidor | FreidorP3-Switch1 | NATR-1783 |  | Switch |  | 100.100.100.61 | 11.18.54.50 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Empaque | EmpaqueP3-PLC | 1768-L43 | 20.18 | PLC | 100.100.100.101 |  | 11.18.54.65 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Empaque | EmpaqueP3-OIT(Host) | IPC2 |  | PC | DHCP | 100.100.100.90 | 11.18.54.66 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Empaque | EmpaqueP3-OIT(VM) | IPC2 |  | PC | 100.100.100.14 | 100.100.100.91 | 11.18.54.67 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
Palitos 3 | Empaque | EmpaqueP3-Switch | 1783-BMS10CGN | 12.005 | Switch |  | 100.100.100.60 | 11.18.54.68 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3

## PC32
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
PC32 | Sazonado | SazonadoPC32-PLC | 1769-L32E | 20.14 | PLC | 130.130.130.101 |  | 11.18.53.31 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Sazonado | SazonadoPC32-HMI |  |  | HMI | 130.130.130.102 |  | 11.18.53.32 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Sazonado | SazonadoPC32-Switch |  |  | Switch | 130.130.130.5 |  | 11.18.53.33 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Descarga | DescargaPC32-PLC | 1769-L33ER |  | PLC | 130.130.130.120 |  | 11.18.53.41 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Descarga | DescargaPC32-HMI |  |  | HMI | 130.130.130.141 |  | 11.18.53.42 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Descarga | DescargaPC32-Switch |  |  | Switch | 130.130.130.140 |  | 11.18.53.43 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Intercambiador | Intercambiador PC32-PLC | 5069-L320ERS2 | 33015 | PLC | 130.130.130.150 |  | 11.18.53.64 | 255.255.255.128 | 11.18.53.1 | VLAN 612
PC32 | Intercambiador | Intercambiador PC32-HMI |  |  | HMI | 130.130.130.153 |  | 11.18.53.65 | 255.255.255.128 | 11.18.53.1 | VLAN 612
PC32 | Linea | PC32-PLC | 1756-L61 | 17.3 | PLC | 130.130.130.100 |  | 11.18.53.55 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Linea | PC32-OIT1 | PC |  | PC | 130.130.130.111 |  | 11.18.53.56 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Linea | PC32-OIT2 | PC |  | PC | 130.130.130.112 |  | 11.18.53.57 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Linea | PC32-APC(Host) | PC |  | PC | 130.130.130.251 |  | 11.18.53.58 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Linea | PC32-APC(VM) | PC |  | PC | 130.130.130.249 |  | 11.18.53.59 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Linea | PC32-Switch | PC |  | PC | 130.130.130.5 |  | 11.18.53.54 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
PC32 | Empaque | EmpaquePC32-PLC | 1769-L32E | 20.14 | PLC | 11.18.53.70 |  | 11.18.53.70 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1

## PC32 Flex
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
PC32Flex | Linea | PC32Flex-Linea-PLC | 1756-ENBT |  | PLC | 130130130110 | 11.18.54.30 | 11.18.54.30 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 5
PC32Flex | Linea | PC32Flex-Linea-OIT1 | PC |  | PC | 130130130112 | 11.18.54.31 | 11.18.54.31 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 5
PC32Flex | Linea | PC32Flex-Linea-OIT2 | PC |  | PC | 130130130113 | 11.18.54.32 | 11.18.54.32 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 5
PC32Flex | Linea | PC32Flex-Linea-OIT3 | PC |  | PC | 130130130114 | 11.18.54.33 | 11.18.54.33 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 5
PC32Flex | Linea | PC32Flex-Linea-APC(Host) | PC |  | PC | 130130130115 | 11.18.54.34 | 11.18.54.34 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 5
PC32Flex | Linea | Proceso PC32 Flex-NATR | SWITCH |  | 1783-NATR | 130130130109 | 11.18.54.36 | 11.18.54.36 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 5
PC32Flex | Linea | PC32Flex-Linea-APC(VM) | PC |  | PC | 130130130116 | 11.18.54.35 | 11.18.54.35 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 5
PC32Flex | Empaque | PC32Flex-Empaque-PLC | 1768-L43 | 20.18 | PLC | 100100100101 |  | 11.18.54.110 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
PC32Flex | Empaque | PC32Flex-Empaque-OIT1(Host) | IPC2 |  | PC | DHCP | 100.100.100.240 | 11.18.54.111 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
PC32Flex | Empaque | PC32Flex-Empaque-OIT1(VM) | IPC2 |  | PC | 100.100.100.140 |  | 11.18.54.112 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
PC32Flex | Empaque | PC32Flex-Empaque-OIT2(Host) | IPC2 |  | PC | 100.100.100.241 |  | 11.18.54.113 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
PC32Flex | Empaque | PC32Flex-Empaque-OIT2(VM) | IPC2 |  | PC | 100.100.100.141 |  | 11.18.54.114 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
PC32Flex | Empaque | PC32-FLEX-EMPAQUE | SWITCH |  | 1783-NATR | 100.100.100.244 | 100.100.100.244 | 11.18.54.115 | 255.255.255.128 | 11.18.54.1 | VLAN 614 | 3
EMPAQUE
PC32Flex | Empaque | PC FLEX NATR EMPAQUE | SWITCH |  |  |  |  | 11.18.55.28 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-1 | BM |  |  | 100.100.100.61 |  | 11.18.55.29 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-1 | BM |  |  | 100.100.100.71 |  | 11.18.55.30 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-1 | TSC |  |  | 100.100.100.21 |  | 11.18.55.31 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 1 | SWITCH |  |  |  |  | 11.18.55.32 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-1 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.33 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-2 | BM |  |  | 100.100.100.62 |  | 11.18.55.35 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-2 | BM |  |  | 100.100.100.72 |  | 11.18.55.36 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-2 | TSC |  |  | 100.100.100.22 |  | 11.18.55.37 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 2 | SWITCH |  |  |  |  | 11.18.55.38 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-2 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.39 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-3 | BM |  |  | 100.100.100.63 |  | 11.18.55.41 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-3 | BM |  |  | 100.100.100.73 |  | 11.18.55.42 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-3 | TSC |  |  | 100.100.100.23 |  | 11.18.55.43 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 3 | SWITCH |  |  |  |  | 11.18.55.44 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-3 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.45 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-4 | BM |  |  | 100.100.100.64 |  | 11.18.55.47 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-4 | BM |  |  | 100.100.100.74 |  | 11.18.55.48 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-4 | TSC |  |  | 100.100.100.24 |  | 11.18.55.49 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 4 | SWITCH |  |  |  |  | 11.18.55.50 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-4 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.51 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-6 | BM |  |  | 100.100.100.66 |  | 11.18.55.53 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-6 | BM |  |  | 100.100.100.76 |  | 11.18.55.54 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-6 | TSC |  |  | 100.100.100.26 |  | 11.18.55.55 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 6 | SWITCH |  |  |  |  | 11.18.55.56 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-6 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.57 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-7 | BM |  |  | 100.100.100.67 |  | 11.18.55.59 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-7 | BM |  |  | 100.100.100.77 |  | 11.18.55.60 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-7 | TSC |  |  | 100.100.100.27 |  | 11.18.55.61 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 7 | SWITCH |  |  |  |  | 11.18.55.62 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-7 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.63 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-8 | BM |  |  | 100.100.100.68 |  | 11.18.55.65 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-8 | BM |  |  | 100.100.100.78 |  | 11.18.55.66 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-8 | TSC |  |  | 100.100.100.28 |  | 11.18.55.67 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 8 | SWITCH |  |  |  |  | 11.18.55.68 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | FLEX-GUACP M-8 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.69 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-9 | BM |  |  | 100.100.100.69 |  | 11.18.55.71 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-9 | BM |  |  | 100.100.100.79 |  | 11.18.55.72 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-9 | TSC |  |  | 100.100.100.29 |  | 11.18.55.73 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 9 | SWITCH |  |  |  |  | 11.18.55.74 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-9 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.75 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS BM M-10 | BM |  |  | 100.100.100.70 |  | 11.18.55.77 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-ATLAS ITPS M-10 | BM |  |  | 100.100.100.80 |  | 11.18.55.78 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-SEAL CHEKER M-10 | TSC |  |  | 100.100.100.30 |  | 11.18.55.79 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC FLEX NATR GUACP 10 | SWITCH |  |  |  |  | 11.18.55.80 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5
PC32Flex | Empaque | PC Flex-GUACP M-10 | GUACP |  |  | 192.168.0.102 |  | 11.18.55.81 | 255.255.255.128 | 11.18.55.1 | VLAN 616 | 5

## Schaaf 1
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Schaaf1 | SprayD | SprayDSchaaf1-PLC | 2085-LC50-24QWB |  | PLC |  | 11.18.53.17 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | SprayD | SprayDSchaaf1-HMI | 2711R-T7T |  | HMI |  | 11.18.53.18 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Ext1200 | Schaaf1-1200-PLC | 1769-L32E | 20.14 | PLC | 192.168.1.102 | 11.18.53.19 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Ext1200 | Schaaf1-1200-HMI |  | 12 | HMI | 192.168.1.101 | 11.18.53.20 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Ext925 | Schaaf1-925-PLC | 1766-L32BXB |  | PLC | 192.168.1.1 | 11.18.53.21 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Ext925 | Schaaf1-925-HMI |  | 5.1 | HMI | 192.168.1.20 | 11.18.53.22 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Mixer1200 | Schaaf1-Mix1200-PLC | MX1400 |  | PLC | 130.130.130.10 | 11.18.53.23 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Mixer1200 | Schaaf1-Mix1200-HMI |  |  | HMI | 130.130.130.11 | 11.18.53.24 |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Sazonado | SazonadoSchaaf1-PLC | 1769-L35E | 17.4 | PLC | 100.100.100.101 |  | 11.18.53.25 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Sazonado | SazonadoSchaaf1-HMI1 | 2711P-T10C4D2 |  | HMI | 100.100.100.102 |  | 11.18.53.26 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Sazonado | SazonadoSchaaf1-HMI2 | 2711P-T10C4D2 |  | HMI | 100.100.100.103 |  | 11.18.53.27 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Sazonado | SazonadoSchaaf1-HMI3 | 2711P-T6C20D2 |  | HMI | 100100100120 |  | 11.18.53.28 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Sazonado | SazonadoSchaaf1-POINT_MARMITA |  |  | IO | 100.100.100.105 |  |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Sazonado | SazonadoSchaaf1-SAZONADO |  |  | IO | 100.100.100.200 |  |  | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1
Schaaf1 | Sazonado | SazonadoSchaaf1-Switch | 1783-BMS10CGN |  | SWITCH |  | 100.100.100.50 | 11.18.53.29 | 255.255.255.128 | 11.18.53.1 | VLAN 612 | 1

## Schaaf 2
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Schaaf2 | Ext925 | Schaaf2-Ext925-PLC | 1769-L33ER | 32.011 | PLC | 192.168.1.11 | 11.18.53.151 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Ext925 | Schaaf2-Ext925-HMI | 2711P-T10C4D8 | 12 | HMI | 192.168.1.12 | 11.18.53.152 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Ext925 | Schaaf2-Ext925-Switch | 1783-BMS10CGN | 9.001 | SWITCH | 192.168.1.40 | 11.18.53.175 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Ext925 | Schaaf2-Ext925-MTR509 | PF525-EENET | 5.001 | VFD | 192.168.1.20 | 11.18.53.153 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Ext925 | Schaaf2-Ext925-MTR550 | PF525-EENET | 5.001 | VFD | 192.168.1.21 | 11.18.53.154 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Ext925 | Schaaf2-Ext925-MTR609 | PF525-EENET | 5.001 | VFD | 192.168.1.22 | 11.18.53.155 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Mixer925 | Schaaf2-Mixer925-PLC | MX1400 |  | PLC | 192.168.1.1 | 11.18.53.156 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Mixer925 | Schaaf2-Mixer925-HMI | 2711R-T4T | 5.011 | HMI | 192.168.1.2 | 11.18.53.157 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Ext1250 | Schaaf2-Ext1250-PLC | 1769-L33ER | 24.11 | PLC | 192.168.1.100 | 11.18.53.158 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Ext1250 | Schaaf2-Ext1250-HMI | 2711P-B10C22D9P | 12 | HMI | 192.168.1.10 | 11.18.53.159 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Mixer1250 | Schaaf2-Mixer1250-PLC | 1769-L24ER-QBFC1B | 24.11 | PLC | 192.168.1.101 | 11.18.53.160 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Mixer1250 | Schaaf2-Mixer1250-HMI | 2711PC-T6C20D8 | 12 | HMI | 192.168.1.201 | 11.18.53.161 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | SprayD | SprayDSchaaf2-PLC | 2085-LC50-24QWB |  | PLC |  | 11.18.53.162 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | SprayD | SprayDSchaaf2-HMI | 2711R-T7T |  | HMI |  | 11.18.53.163 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-PLC | 1769-L32E | 20.12 | PLC | 192.168.1.100 | 11.18.53.164 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-HMI | 2711P-T10C4D8 | 12 | HMI | 192.168.1.121 | 11.18.53.165 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-TR_SAL_HORNO1_DER | PF525-EENET | 5.001 | VFD | 192.168.1.103 | 11.18.53.166 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-TR_SAL_HORNO1_IZQ | PF525-EENET | 5.001 | VFD | 192.168.1.104 | 11.18.53.167 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-ALIM_ELEV_EMPQ | PF525-EENET | 5.001 | VFD | 192.168.1.105 | 11.18.53.168 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-VF_RESERVA_01 | PF525-EENET | 5.001 | VFD | 192.168.1.106 | 11.18.53.169 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-SALIDA_TAMBOR | PF525-EENET | 5.001 | VFD | 192.168.1.107 | 11.18.53.170 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-VF_RESERVA_02 | PF525-EENET | 5.001 | VFD | 192.168.1.108 | 11.18.53.171 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Horno | Schaaf2Horno-REMOTA_HMI | 1734-AENTR |  | IO | 192.168.1.120 | 11.18.53.172 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Empaque | EmpaqueSchaaf2-PLC | 1768-ENBT |  | PLC | 100100100101 |  | 11.18.53.176 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Empaque | EmpaqueSchaaf2-OIT(VM) | IPC2 |  | PC | 100.100.100.12 |  | 11.18.53.177 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Empaque | EmpaqueSchaaf2-OIT(Host) | IPC2 |  | PC | 100.100.100.11 |  | 11.18.53.178 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Empaque | EmpaqueSchaaf2-NATR | 1783-NATR |  | SWITCH |  | 100.100.100.51 | 11.18.53.179 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
Schaaf2 | Empaque | EmpaqueSchaaf2-Switch | 1783-BMS12T4E2CGL |  | SWITCH |  | 100.100.100.50 | 11.18.53.180 | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2

## Tanques Azules
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
Tanques Azules | Tanques Azules | TanquesAzules-PLC | 1763 | 9.05 | PLC | 192.168.0.9 | 11.18.54.139 |  | 255.255.255.128 | 11.18.54.129 | VLAN 615 | 4

## WWTP
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
WWTP | WWTP | WWTP-PLC | 1769-L33ER | 20.13 | PLC | 120.120.120.10 |  | 11.18.54.141 | 255.255.255.128 | 11.18.54.129 | VLAN 615 | 4
WWTP | WWTP | WWTP-SCADA |  |  | PC | 120.120.120.8 |  | 11.18.54.142 | 255.255.255.128 | 11.18.54.129 | VLAN 615 | 4
WWTP | WWTP | WWTP-HMI |  |  | HMI | 120.120.120.9 |  | 11.18.54.143 | 255.255.255.128 | 11.18.54.129 | VLAN 615 | 4
WWTP | WWTP | WWTP-Switch | 1783-BMS10CGN |  | SWITCH |  | 120.120.120.50 | 11.18.54.144 | 255.255.255.128 | 11.18.54.129 | VLAN 615 | 4
WWTP | WWTP | WWTP-PLC-RECUPERO | 1763-L16BWA | 14 |  | 120.120.120.100 |  | 11.18.54.145 | 255.255.255.128 | 11.18.54.129 | VLAN 615 | 4

## TC2000
Linea | Area | Equipo | Módulo | FW | Tipo | IP original | IP nueva | IP Pública | Máscara nueva | Gateway | VLAN | IDF
TC2000 | Cocimiento | TC-2000-PROCESO-NATR | 1756-ENBT |  | NATR | 130.130.130.1 | 11.18.53.141 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Proceso | TC2000-PLC LBCSS1 | 1756-ENBT |  | PLC | 130.130.130.5 | 11.18.53.142 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Cocimiento | TC2000-PLC PROCESO | 1756-ENBT |  | PLC | 130.130.130.6 | 11.18.53.143 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Proceso | TC2000-OIT-LBCSS1 | PC |  | PC | 130.130.130.10 | 11.18.53.144 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Proceso | TC2000-OIT-OVEN | PC |  | PC | 130.130.130.11 | 11.18.53.145 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Proceso | TC2000-OIT-SEASONING | PC |  | PC | 130.130.130.12 | 11.18.53.146 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Proceso | TC2000-PC-APC | PC |  | PC | 130.130.130.13 | 11.18.53.147 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Proceso | TC2000-PLC-RADAR | PLC |  | PLC | 130.130.130.8 | 11.18.53.148 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Proceso | TC2000-OIT-RADAR | PC |  | PC | 130.130.130.9 | 11.18.53.149 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Enzimas | TC2000-PLC Enzima | 1769-L27 |  | PLC | 130.130.130.14 | 11.18.53.190 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | Enzimas | TC2¦000-HMI Enzima | PVPlus 7 |  | HMI | 130.130.130.14 | 11.18.53.191 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | spray dinamics | TC2000-PLC spray dinamics | 5069-L320ERS |  | PLC | 130.130.130.15 | 11.18.53.192 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2
TC2000 | spray dinamics | TC2000-HMI spray dinamics | PVPlus 7 |  | HMI | 130.130.130.16 | 11.18.53.193 |  | 255.255.255.128 | 11.18.53.129 | VLAN 613 | 2